JISC Final Report

| Project Information |  |  |  |
| --- | --- | --- | --- |
| Project Identifier | To be completed by JISC |  |  |
| Project Title | Arts Learning and Teaching Online UK (ALTO UK) |  |  |
| Project Hashtag | ALTOUK |  |  |
| Start Date | 17 October 2011 | End Date | 31 July 2012 – extended to 31 August |
| Lead Institution | University of the Arts London (UAL) |  |  |
| Project Director | Nancy Turner |  |  |
| Project Manager | John Casey |  |  |
| Contact email | j.casey@arts.ac.uk |  |  |
| Partner Institutions | - HEA ADM Subject Centre - Herriot Watt University, The School of Textiles and Design - Jorum Service, MIMAS, University of Manchester - Kirklees College, Creative Industries, Ceramics - University of Brighton, Faculty of Arts, Broadcast Media - Bloomsbury Publishing Plc - Laurence King Publishing Ltd. - Bright Lemon Ltd., London |  |  |
| Project Web URL | http://blogs.arts.ac.uk/alto/ http://process.arts.ac.uk http://alto.arts.ac.uk/filestore/ |  |  |
| Programme Name | Open Educational Resources (OER) Phase Three Programme: Embedding and Sustaining Change. Strand 4 - OER Themes |  |  |
| Programme Manager | David Kernohan |  |  |

| Document Information |  |  |  |
| --- | --- | --- | --- |
| Author(s) | John Casey |  |  |
| Project Role(s) | Project Manager |  |  |
| Date | 15/12/12 | Filename | ALTO UK Final Report.doc |
| URL | http://alto.arts.ac.uk/1009/ |  |  |
| Access | This report is for general dissemination |  |  |

| Document History |  |  |
| --- | --- | --- |
| Version | Date | Comments |
| 1 | 27/8/12 |  |
| 2 | 28/9/12 |  |
| 3 | 15/12/12 |  |

Table of Contents

1

1	Acknowledgements	3

2	Project Summary	4

2.1	Project Outputs and Outcomes	5

2.2	How did we go about achieving our outputs / outcomes?	9

2.2.1	Aims	9

2.2.2	Objectives	9

2.3	Project methodology	10

2.4	What did we learn?	10

2.4.1	Challenges and Adjustments	11

2.4.2	Unanticipated Outcomes	11

2.4.3	Research activities	14

2.4.4	User testing	14

2.5	Immediate Impact	15

2.5.1	What kind of difference has the project made to our partner institutions?	15

2.5.2	How has the wider community benefitted from our project?	16

2.5.3	What evidence do we have for this?	17

2.5.4	How has the project changed the attitudes of our stakeholders?	17

2.6	Future Impact	17

2.6.1	Who/What will be impacted?	17

2.6.2	Tracking this impact?	18

3	Conclusions	18

3.1	General conclusions	18

3.1.1	OER/P as a Driver for Change	18

3.2	Conclusions relevant to the wider ADM community	19

3.3	Conclusions relevant to JISC / HEA	20

4	Recommendations	20

4.1	General recommendations Arising from the Project - UAL	20

4.2	Recommendations for working with the wider ADM community	20

4.3	Recommendations for JISC	20

5	Implications for the future	21

6	Appendices	22

6.1	Brighton OER Study	22

6.2	ALTO UK / DIAL Open Educational Practice Update	23

6.3	ALTO UK Evaluation Report	23

6.4	HEA International OER Collaboration Study	23

# Acknowledgements

We would like to acknowledge the following:

- The Open Educational Resources (OER) Phase Three Programme: Embedding and Sustaining Change. Strand 4 - OER Themes - for funding this project.

- Our evaluation ‘buddy’ Vivien Rolfe from the De Montfort University HALSOER OER Phase 3 Project for comment about our Open CourseBook Format, discussion and advice about Search Engine Optimisation (SEO) and about working with publishers.

- The ad hoc and ‘working with commercial publishers’ evaluation group from Strand 4

- The OER Phase 3 Evaluation and Synthesis project for comment, guidance and convening some very useful online discussions and providing the evaluation toolkit, which we have found very useful.

- Our project partners:

  - HEA ADM Subject Centre University of Brighton. Advice and assistance about using the ADM centre focus group methodology and tools. Helping with designing focus groups in the UAL. Organizing an in-depth study at Brighton University and organizing the UK Arts OER conference - Drawing on All Resources. Prof. Stuart Laing, Deputy Vice Chancellor, Dr. Stephen Mallinder: Researcher-Projects Manager, Debbie Flint, Educational Developer, Jennie Embleton, Administrator, Sarah Atkinson, Digital Media lecturer, Faculty of Arts, Broadcast Media.

  - Herriot Watt University, The School of Textiles and Design. Providing content in the subject areas of Fashion and Textiles and contribution to workshops. Prof. Alison Harley, Head of School, Theresa Coburn, lecturer, Sarah Taylor, lecturer Madeleine Sclater, Director for Learning and Teaching, and of course the students named in the Open CourseBook

  - Jorum Service, MIMAS, University of Manchester, Providing a repository for content and advice on linking. Sarah Currier, Service Manager

  - Kirklees College, Creative Industries, Ceramics. Providing content relating to Ceramics. June Durrant, Director of Curriculum for Higher Education, Mark Clough lecturer and of course the students named in the Open CourseBook

  - Bloomsbury Publishing Plc. Provide content from current catalogue. Kathryn Earle, Head of Academic Publishing, Bloomsbury. Davida Forbes Editor – content selection, development of linking protocols and design of PDF excerpt formats.

  - Laurence King Publishing Ltd. Provide content from current catalogue. Philip Cooper, Editorial Director, – content selection and development of linking protocols and scoping of future shared video productions

- Manda Helal, Camberwell College (UAL) Ceramics tutor. Providing content relating to Ceramics contribution to workshops and advice about Open CourseBook format design, liaison with past students, and of course the students named in the Open CourseBook

- Bright Lemon Ltd., London. Consultancy for the use of social media and Drupal development for redesign of the Process.Arts web site. Leon Tong, Director, Piotr Klarowski, junior designer.

- Teaching and support staff at the UAL for taking the time to engage with the project team

- Marc Griffith, CLTAD VLE Co-ordinator (UAL) for comment and input into the development of the Open CourseBook format and related storage options and developments

- The original designers and developers of the Process.Arts social software (Chris Follows, Mike Kelly & Paul Tabak)

- The UAL legal Department (Frances Graupner and Paul Morruzi) for legal advice and support

- Pat Christie, UAL Librarian and Chair of Project Board. External project board members for valuable suggestions and comments

# Project Summary

The project was initiated by and based in the UAL Centre for Learning and Teaching in Art and Design (CLTAD) with the express aim of helping to drive cultural change and awareness across the UAL and its partner institutions, in relation to the benefits of creating, sharing and using OERs and developing the associated Open Educational Practice (OEP). In this respect it has achieved success in acting as a lightening rod around which a number of diverse discussions have begun in areas including IPR policy and awareness, digital literacy, developing staff skills in instructional design, bridging the gap between managing learning resources (as OERs) and research data and outputs in HE, and exploring personal and disciplinary differences in educational philosophy.  These areas are explored further in the body of this report and the Appendices.

ALTO UK was a project that was part of the Open Educational Resources (OER) Phase Three Programme: Embedding and Sustaining Change, Strand 4 - OER Themes. We chose to tackle a wide spread of themes. In some ways this mirrors the broad spread of activities at art colleges and current concerns e.g. foundations courses as FE prior to entering Art College, the relationship with arts education and commercial publishers extends beyond educational textbooks into ‘consumer products’, ‘making’ courses in the crafts are under economic pressure as they are expensive to teach and we needed to investigate the possibilities there. We felt a broad spread of activities might provide a richer picture of the possibilities that OERs might provide for arts education.

Section 2.4.2 describes the unanticipated outcomes arising from the project, of which there have been quite a few, one ‘standout’ outcome has been the notion of using OER to drive research impact ratings.

The strand 4 Themes projects were funded to investigate the use of OER approaches as a means to work towards particular strategic, policy and societal goals. The ALTO UK project was involved in investigating the following themes:

Theme A: Extend OER through collaborations beyond HE

- Element 1: Work with another sector of education/training (FE)

Theme B: Explore OER publishing models

- Element 1: Collaboration with commercial publishers.

- Element 2: Using a range of openly licensed collections of materials as the basis for new resources.

Theme C: Addressing sector challenges

- Element 3: Enabling Sustainable Economic Practice.

- Element 4: Preserving the breadth of UK higher education in a time of consolidation.

Theme D: Enhancing the student experience (working with the UAL DIAL project to support the creation of OERs)

- Element 1: Resources to support university applicants.

Main Body of Report

## Project Outputs and Outcomes

| Output / Outcome Type (e.g. report, publication, software, knowledge built) | Brief Description and URLs (where applicable) |
| --- | --- |
| OERs produced | - Introduction to Woven Textiles Open CourseBook - http://alto.arts.ac.uk/974/ - Foundation Ceramics Open CourseBook - http://alto.arts.ac.uk/975/ - Fashion Communication-Photography Open CourseBook - http://alto.arts.ac.uk/977/ - Basic Ceramics Skills Open CourseBook - http://alto.arts.ac.uk/976/ - ALTO UK Open Course Book Template and Rationale - http://alto.arts.ac.uk/930/ - Derek Boshier: From Doris To Chemical Cowboys - http://alto.arts.ac.uk/876/ - Creative Commons Licences – are they right for you? - http://alto.arts.ac.uk/904/ - Introducing Pottery Chapters 2&3 (Bloomsbury Publishing due for release 2012) - http://alto.arts.ac.uk/914/ - IPR e –Content Audi and Risk Evaluation Matrix - http://alto.arts.ac.uk/950/ - Cloud Services for Large Scale Open Educational Resources Publishing: A Feasibility Study for the ALTO UK Project - http://alto.arts.ac.uk/946/ - Amazon Web Services Training Guide - http://alto.arts.ac.uk/949/ - PDP planner - http://www.arts.ac.uk/ppd/ - Collaboration with ‘Satellite Voices’ the international arm of the online magazine ‘Dazed and Confused’ An international video ‘chain letter collaboration between students. Students from UAL collaborate with students at other art colleges in Tokyo, Moscow, Shanghai, Paris and Dubai and collaborate on a virtual project together - http://www.dazeddigital.com/satellitevoices/ - Background http://www.dazeddigital.com/artsandculture/article/13596/1/satellite-voices-connects-with-central-saint-martins - Student Outputs at: http://process.arts.ac.uk/category/tags/satellite-voices - Series of short films about objects from the Jocelyn Herbert Archive presented by leading figures from theatre and film and (in production for delivery in late 2012 |
| OERs produced in association with the UAL DIAL Digital Literacy project funded by JISC | - OER over 90 resources about Open Educational Resources, majority produced through the SCORE fellowship - OER arts resources OER related content specifically within the art & design practice based subjects - SCORE dissemination 20 plus conference recording, lecture notes and papers of my SCORE dissemination - Open practice Focus here is on open practice and communities and less on OERs - Reuse 100 resources including web tools, websites, reuse stories and experiments - Copyright issues A really interesting & developing batch of resources exploring, IPR, appropriation & CC licenses - Learning video research a new area currently being developed and populated by new individuals and projects |
| Pilot exploration of a shared social media platform for UK HEI Art & Design HEIs | - Institutional spaces inside the current Process.Arts platform - http://process.arts.ac.uk/category/discipline/research-practice/alto-uk - Prototype of a shared UK platform - http://prototype.cloudylemonade.net/ual/v4/ |
| Use of student video testimonies supported by heir sketchbooks to illustrate ‘invisible’ learning processes | Video Sketchbooks Examples: - http://alto.arts.ac.uk/979/ - http://www.Youtube.com/watch?v=WtpJBXud7qE&feature=plcp |
| Use of video to illustrate technical and procedural aspects of the courses | Technical Process Demonstration Videos Examples: - http://www.youtube.com/watch?v=6qloUCnUM7I (no sound) - http://process.arts.ac.uk/content/loss-wax-process-introduction-bronze-casting-part-one |
| Reconceptualising traditional art & design teaching for flexible and blended delivery | Partners at Kirklees College and Herriot Watt University School of Textiles and Design are redesigning courses based on the experiences gained in this this project |
| 1 Day National UK Arts OER conference | Arts OER conference ‘Drawing on All Resources’ - Open Educational Practice Forum May 16 (OERs in the ARTS), convened as part of ALTO UK project, Brighton University. For more information and presentations please visit this link |
| Prototype of a UK Art & Design OER publishing platform for HEIs | online at: - http://prototype.cloudylemonade.net/ual/v4/ |
| Linking protocol for commercial publishers content release formats for embedding in Open CourseBooks and web pages – based on MIT OCW | Completed, waiting for publisher feedback available at: - http://alto.arts.ac.uk/981/ |
| Commercial publishers content release formats in PDF format | Completed, waiting for publisher feedback available at: http://alto.arts.ac.uk/914/ Test login account to view is (ID = Teacher1, pass = test) |
| Development of simple authoring tools to support sustainable engagement with OER creation by teaching staff | Open CourseBook format was developed to support busy teachers with limited IT skills author OERs. Initial prototypes and testing in Word and PDF formats, for authoring and delivery. Second phase of development underway to create HTML5 authoring tool prototype – due for delivery late 2012. |
| OER authoring tool design discussions with international advisory group members | Follow on activity with HEA funding starting – please see Appendix for project proposal |
| New UAL course handbook design influenced by ALTO UK Open CourseBook format | The simplicity of the format makes it more usable at conveying essential information quickly – currently under development at the UAL |
| Bradford FE College to trial Open CoursBook format in their VLE | Colleagues at Bradford College have asked to use the Open CoursBook Template as the basis for a resource design tool to improve design and management of learning resources |
| OER creation as a diagnostic tool for assessing digital literacy needs | OER creation encapsulates many underlying issues and challenges in HE (both ‘hard’ tech factors and ‘softer’ cultural factors). In relation to digital literacy needs analysis and assessment, the task of creating OERs as Open CourseBook (for example) provides a useful diagnostic tool and a context for taking remedial and developmental measures. |
| Example of Jorum Content directly linked to from Process.Arts (and web pages) by ‘deep linking’. | Prototype example of using a social media platform to provide feeds for community ‘lenses’ into the Jorum and other repository collections – a basic visualisation prototype is available at this address http://www.digitalinsite.co.uk/jorum/ (while the Process.Arts site is undergoing redevelopment) |
| First iteration of Terms and Conditions capable of supporting a shared UK service | http://alto.arts.ac.uk/filestore/terms.html |
| University of Brighton Institutional OER study | Appendix to this Report |
| UAL/Heriot Watt/Kirklees Focus Group and Workshop Report | Appendix to this Report |
| Formation of UAL Open Education Practice Steering Group with senior management members | First meeting held in September |
| Nomination of Process.Arts to the People’s choice Awards for free educational resources under the ‘Most Progressive’ category. | http://education-portal.com/articles/Education-Portalcom_Peoples_Choice_Awards_Nominees.html |
| New UAL Moodle development to feature default ‘open share options’ | The new UAL Moodle installation is to have a default setting on all courses to share across the UAL (promoting a culture of sharing) and to be linked the UAL OER repository for easy deposit under CC licences |
| New study module in Open Educational Practice for the UAL PG Cert. in HE Teaching | As a result of the ALTO UK project CLTAD felt confident enough to apply for HEA/JISC funding to develop a new study module in Open Educational Practice for the UAL Continuing and Professional Development Framework and PG Cert. in HE Teaching. Course Handbook is here: http://oepractice.myblog.arts.ac.uk/2012/08/15/oep-unit-handbook/ |
| Involvement in HEA OER international business opportunity study | Follow on activity with HEA funding – please see Appendix for project proposal |
| Publications and Conference Presentations etc. | - ‘Open Networks for Culture and Education’, (Long Paper) A roadmap for future development. ECLAP 2012 Conference on Information Technologies for Performing Arts, Media Access and Entertainment, 7-9 May 2012, Florence, Italy. available at http://alto.arts.ac.uk/943/ - ‘Cloud Services for Large Scale Open Educational Resources Publishing: A Feasibility Study for the ALTO UK Project’. February 2012 http://alto.arts.ac.uk/946/ - ‘Creative Commons Licences: are they right for you?’ in Arts Libraries Journal special edition on copyright Vol 37, Number 2, 2012, ARLIS/UK (Victoria and Albert Museum), London (see http://alto.arts.ac.uk/904/). - ‘Collaborative Learning Design’ shared approaches to designing OERs and the Open Coursebook format (Appears in issue 18 of Networks link). Part of the Brighton University Arts OER conference ‘Drawing on All Resources’ - Open Educational Practice Forum May 16 (OERs in the ARTS), convened as part of ALTO UK - Disciplinary and Institutional Perspectives on Open Educational Practice in Art, Design and Media Studies: Opportunities and Challenges, OCWC / OER 2012 conference Cambridge, video presentation is available here text available at http://alto.arts.ac.uk/947/ - ‘The ALTO Ecosystem Model: Open Spaces for Arts Education’, Designs on E-Learning conference 2011: Future Learning Spaces, 2011, September, Helsinki. -, available at http://alto.arts.ac.uk/945/. - ‘The Arts Vs OER: Institutional collaboration for curriculum development’. The National Society for Education in Art and Design Conference October 2011: The Centrality of Art, Design and the Performing Arts to Education. Chester. Available at http://alto.arts.ac.uk/948/ - Submissions: - ‘Taking Care of Business: Enterprising Approaches to Openness and Sharing in Education’, ALT – C 2012, Manchester presentation - ‘Collaborative Learning Design – A Solution to the Crisis in Art Education’, Designs on E-Learning conference 2012: Cloud and Crowd, September, London available http://alto.arts.ac.uk/982/ - ‘Open Educational Resources and Practices as a Driver for Change in Art College Education’. Presentation and Workshop at the Open Education 2012 conference Vancouver, October 2012 |

## How did we go about achieving our outputs / outcomes?

### Aims

The aim of this ambitious short project was the creation of both ‘Collect’ and ‘Release’ types of OERs in relation to the identified Strand 4 Themes and Contexts described in the project summary above. The key aims outlined below were really driven by some pressing needs being experience in the art and design education community, funding cuts, specialist craft subjects under pressure, the need to be able to have an online presence to showcase our work and collaborate nationally and globally and ‘prospect’ future possibilities. The end user groups for this project were art and design staff and students in the project partners and other institutions as well as independent learners. The project was built on existing relationships between the partners and was characterised by strong collaboration between HE institutions, commercial publishers, the FE sector, a JISC digital literacy project based at the UAL (DIAL), as well as the wider OER community. The project featured appropriate and realistic technical innovation to support the project aims and objectives.

Key project aims were to:

- Release learning resources with an emphasis on endangered subjects (disciplines which are in decline for a number of reasons – usually those involved with ‘making skills’ such as textiles, ceramics, etc. that are expensive to teach) and student transitions. The project identified and released content related to ceramics, weaving and textile design and fashion communication.

- Carry out a small pilot exercise with each partner with an institutionally branded open space in a social media platform to share OERs (http://process.arts.ac.uk/). The platform is based on the popular open source web content management system Drupal (http://drupal.org/) and provides a user-friendly interface, rich media tools and easy integration with the rest of the Web 2.0 infrastructure such as Twitter, Facebook and Google etc. A longer-term aim was also to explore the feasibility of extending such a service to support other UK art and design HEIs.

- Work with commercial publishers to release some of their content as OERs

- Work with an international advisory group to identify future development opportunities and advise on emerging solutions being developed by the project

### Objectives

Key project objectives were to:

- Create and release OERs by:

  - Co-creation of resources with academics in FE and HE partner institutions

  - Negotiation of release of content from commercial publishing partners

- Through these activities address sector challenges of:

(a) Sustainability by preserving knowledge and teaching methods of endangered subjects that may otherwise be lost to the post-secondary sector.

(b) Engaging academics in art and design in the exploration of alternative teaching techniques including flexible and blended learning models

- Enhance deposit and use of OERs in art and design by creating a prototype shared dynamic collaborative social media based platform based on the experience of Process.Arts at the UAL which:

(a) Is linked to Jorum.

(b) Has clear policies of use for the project partners and potentially the wider HE sector.

(c) Is integrated into the wider OER ecosystem

- Explore, with the UAL DIAL digital literacy project, how creation and use of OERs can contribute to the digital literacy of staff and students in art and design

- Support the transition of students into HE art and design by making stimulating and visually engaging OERs in these subject areas accessible to potential students to help them make more informed choices

- Developing a roadmap for future developments for international use, through collaboration with an international expert advisory group

## Project methodology

We adopted the techniques of using focus groups used by the Brighton ADM subject centre to get an idea of what out stakeholders thought about OER and what their existing attitudes and practice was in relation to sharing and reuse. We also sought to explore their understanding of the open agenda and related issues such as Copyright awareness and their use of any tools and services. In addition we held a series of workshops with teachers to help them develop OERs with their students and find out more about how they work and what barriers and enablers they experienced to their engagement with OER.

We have been influenced by the socio-technical design tradition (Mumford, 1995), that has an ethnographic approach that stresses the need to understand how people really live, and work in order to design and develop appropriate and useful tools and solutions to meet their needs. Two recent interpretations of this tradition for system design and development have been useful, notably by Sharples (2002) as ‘Socio-Cognitive Engineering’ and Wenger (1995 & 2009) as ‘Communities of Practice’ and ‘Technology Stewards’.

By taking these approaches we were able to gather a lot of rich and detailed information about how people worked and their attitudes, values, fears and hopes in relation to education, sharing and technology. We also discovered a lot about individual pedagogic models and assumptions as well as views about how education is currently organised and delivered in the partner institutions.

For evaluation, we broadly followed the evaluation plan as set out in the project plan but did not use surveys or evaluation forms, relying much more on focus groups, discussions, interviews and observations. We felt this was a much more useful way of evaluating things, given the low levels of awareness and the range of soft issues we encountered in relation to issues surrounding sharing, job security, digital literacy and confidence. This helped us to conclude that teachers in our target groups needed assistance with digital skills and confidence in relation to OER creation and also needed some sort of conceptual and practical framework to operate within.

Our engagement with project stakeholders was mainly through the use of focus groups to kick things off followed up by discussions, interviews, meetings and workshops, with more traditional, academic engagement through participation in conferences, workshops and publications. Through the Web 2.0 channels we used the Process.Arts platform to make links and hold discussions.

Technical development was broadly based on agile approaches and the Socio-Cognitive Engineering approach to explore user behaviours, with an emphasis on creating early prototypes and testing with users. This helped us to decide to devise and test authoring tools (Open CourseBook) and create an early Drupal shared service prototype which has progressed our understanding in this area considerably. Based on the reaction to authoring tool prototype work, as well as difficulties in sourcing a Drupal developer in the UAL, it was decided to concentrate of our development efforts on the authoring tool and commence work on a HTML5 based version.

## What did we learn?

The project was ambitious given the range and scale of the different activities in the short timescale as well as the differences in teaching that exist in the practice based disciplines of art and design in contrast to more ‘academic’ subjects.  Much of the teaching is studio and workshop based and involves a mentoring relationship between teacher and student rather than more traditional didactic methods which, arguably, lend themselves more easily to the standard model of OER content creation (as exemplified by MIT OCW). What we envisage developing through our work in ALTO UK is a rich model for the co-design and publishing of OERs in practice-based arts subjects that, we hope to take forwards in further institutional and collaborative research and development projects. The working title for this is model is ONCE (Open Networks for Culture and Education), which aims to create a reusable and adaptable model for providing appropriate technical, cultural and policy support for OER development and collaboration in the Art and Design sector for further information and a proposed roadmap for future development please see http://alto.arts.ac.uk/943/.

### Challenges and Adjustments

The art college sector has been particularly hard hit, together with the humanities in general, by the government higher education budget cuts, which has removed most of the support for teaching and a substantial amount for research in the arts.

The effect of this was felt in the project almost from the start with all the academic partner institutions experiencing reorganisations and redundancy programmes. It is indicative of the situation that all of the academic participants named in the acknowledgements section of this report actually experienced the threat of workplace reorganisation and redundancy and half of them were actually made wholly or partly redundant from their jobs during the timescale of this project. That the project has made the progress it is has is a testament to their professionalism and commitment.

Due to this situation we decided to adopt an agile and flexible method of working and planning. In hindsight, what began as a way of dealing with unexpected challenges encouraged us to take a more enterprising and opportunist approach. As a result we did not cover the range of subject disciplines that we set out to; drawing and painting were dropped from the UAL agenda and digital media from Brighton, who opted for a more in-depth institutional study. In in our software development activities we redirected some of our resources from Drupal development into authoring tool design and prototyping activities that has led to the Open CourseBook format and the current development of HTML5 authoring tools.

### Unanticipated Outcomes

Responding to the Challenges of the ADM sector

These unanticipated outcomes have come about largely as a result of our responses to the challenges that the Art and Design and Media sector presents to OER engagement. These include:

- Pedagogic cultures that can, in some cases, tend to be conservative, with access to, and use of technology limited, IT skills and confidence are often low, institutional support and IT infrastructure capacity can be limited.

- Much of the teaching is studio-based and involves a mentoring relationship between teacher and student rather than more traditional content-centric didactic methods which lend themselves more easily to the standard model of OER content creation. So, there is a need to capture and represent the hidden and invisible elements of teaching and learning that occurs during these courses in a useful and meaningful way

- Creating OERs (and models for future production) for ‘endangered’ subjects that are in danger of ceasing to be taught in the UK, such as weaving and ceramics.

In trying to find answers to these challenges we were inspired by the ideas around frugal innovation, and we held a series of focus groups and workshops with participants to explore different options. As a result we came up with these solutions/responses:

Open CourseBook

The authoring and distribution tool we devised as a way of dealing with these challenges has been well received. It is based on a hybrid between 2 existing well-established OER distribution formats that also maximises their benefits:

- MIT OCW, which has the virtue of providing a simple, consistent and reasonably intuitive way of representing an academic course.

- The Open Textbook concept, which has the advantage of using a well-understood authoring metaphor – the ‘book’, together with the ability to be distributed in PDF format so that it ‘plays’ on nearly all platforms and operating systems.

This has the following advantages:

- Enables the easy reuse of existing of course information and documentation

- Provides a contextual and pedagogic ‘container’ to hold the supporting resources (texts, images, videos, web resources, textbook extracts etc.)

- Has a relatively low technical threshold (uses Word for authoring)

- Can be accessed online but also downloaded and used offline – an important consideration.

- Importantly, the metaphor of the book is easily understood by teachers and can be used to tell the ‘story’ of the course’, with the use of the timeline providing the narrative arc.

- The production of an Open Coursebook involves specifying the course aims, objective, learning outcomes and assessment criteria etc. – all available from existing internal documentation. It also records what happens when, where, with whom and what resources are involved – all essential elements of the IMS Learning Design specification. But also essential elements required to ‘capture’ a course in order to redesign it for flexible delivery

- It provides a gentle introduction to the design skills needed to support flexible delivery

Using Video to Capture and Share Workshop and Studio Processes

The availability of cheap high quality digital video cameras that can produce HD outputs together with free distribution platforms such as YouTube and Vimeo have made it possible to capture and share studio and workshop processes and techniques that students and teachers can refer to in a flexible manner (at a time and place of their choosing). The work done by Herriot Watt University School of Textiles and Design is a good example of how effective this can be; link. These techniques are now being used increasingly at UAL, Heriot Watt University and at Kirklees College to document and share processes and support flexible learning by students. The practical demonstrations and training sessions with students still happen, but these videos are a way of supporting student revision and learning where technical support staffs are now in shorter supply due to the cutbacks.

The Video Sketchbook

The idea here is that the ‘invisible’ 1-2-1 learning and group work that typically occurs in an Art and Design course can be represented by student testimonies about their experiences using their sketchbooks as prompts (the ‘video sketchbook walkthrough’) as well as talking about their own produced artworks. This can be done by the students themselves as shown here link, or in conjunction with a tutor – a kind of video ‘walkthrough’ where the student and tutor talk about the work and the course – this example link provides a good description of a student and tutor discussing progress from initial ideas through to a finished product. Some educationalists recognise this method of learning as ‘vicarious learning’ i.e. learning through the experience of others (Mayes et al, 2001).

OER as a Digital Literacy Diagnostic Tool

The link between OER engagement and digital literacies has been recognised in the course of the JISC/HEA OER programmes. At the interim programme meeting in 2012 during a group discussion we proposed that OER creation, sharing and reuse could provide a useful diagnostic tool to assess individuals and groups digital literacy needs, and potentially that of institutions as a whole. The UAL JISC digital literacy project (DIAL) worked closely with ALTO UK and developed a very useful way of categorising open educational practice and this link provides an explanation. The DIAL open educational practice interim report in the Appendix gives more information about the collaboration between the 2 projects.

One of the striking experiences in our workshops, that involved developing Open CourseBooks, was the way that they worked as a very effective means of ‘surfacing’ personal digital literacy needs. This could be put to good use by incorporating OER creation into both staff and student training and project work to act as a diagnostic tool. Based on our experiences in these workshops and the previous Phase 2 UAL OER project we think that the need and demand for this type of up-skilling is too large to be met by traditional central training units – who are already under great pressure. Instead, we think that developing a cadre of ‘fieldworkers’ (staff and students) who are trained up to hold informal workshops to create OERs and encourage OEP is likely to be more effective. This seems to fit well with some of the ideas emerging from the JISC Curriculum Design Programme and Helen Beetham’s conceptualisation of a co-curriculum, especially from a digital literacy angle. The practical and informal nature of such workshops allows for just-in-time learning taking place in a low-stress environment and, we have found, it also provides a useful venue for significant amounts of peer-to-peer learning and confidence improvement. The fact that the outputs of the workshops are published online is also a significant factor for motivation and allows participants to refer to them as their own published work in the future.

Such a development programme could be supported by online resources, aggregating content from existing JISC project outputs and JISC Infonet as well other open resources. Plus a, proposed, UAL ‘how to’ handbook for OER in the arts that staff and students could refer to before, during and after the workshops that could even help people to develop their own workshops. This activity could be supported by relatively small amounts of money. This approach has a lot in common with ethnographical approaches to successful socio-technical systems development as advocated by Edith Mumford (1995), Mike Sharples (2006) and Ettiene Wenger (2009). The combination of fieldworkers attached to a central educational development  department like CLTAD to promote OER creation and publishing could provide a model for an economically sustainable means of enhancing both digital literacy and educational development in HE in a time of austerity.

OER/P as a Driver for Rescuing Endangered Subjects

It was striking that in the workshops for creating our OERs for Weaving and Ceramics that we seriously discussed how such subject courses could be converted for flexible delivery, prior to this, these staff had never considered this as a serious possibility – a measure of how traditional much of the pedagogic thinking can be in art colleges in general. In North America low residency masters arts degrees are well established in the ‘making’ subjects including ceramics, although there are few at undergraduate level. Of course, in the UK there is the Open College of the Arts that is delivering open and distance learning degree courses in arts subjects, including in practical subjects like sculpture.

Some interesting recent discussions about what OER/P might do to help endangered arts subjects includes the following early ideas:

- Create a generic foundation course for the subject with the collaboration of several institutions to act as an online national ‘knowledge bank’ to preserve knowledge and teaching techniques in the subject for the future

- Work with practitioner communities and schools and colleges etc. to provide access (for a moderate fee) to workshops and studios and instruction to help independent learners to ‘work through’ the practical aspects of the course

- Learners keep a blog as their online portfolio and sketchbook

- Learners pay a moderate fee to:

  - Receive guidance and tutoring in the subject

  - Have their work assessed and are awarded a certificate and online ‘badge’ by participating institutions that can count towards applying to a formal arts education course

The idea of using community facilities to deliver a low-residency practical course is by no means a new one. The Northern College in Thurso at the northern tip of Scotland offers a part time HNC in equine management that makes use of access to stables across Scotland arranged through contacts with the practitioner community.

Although at first sight this proposal might seem radical, it might prove a powerful way of strengthening links between colleges and practitioner communities in a way that can be mutually beneficial and preserve these subjects into the future.

OER/P as a Tool to Improve Research Impact

Another useful outcome from the interim programme meeting and online evaluation group discussions has been the growing realisation that OER/P can be a powerful way of improving research impact ratings – an important factor in the new funding regime. By incorporating research outputs into OERs researchers can reach much wider potential audiences and have their work picked up by other media networks (such as print and broadcast), which in turn multiplies the impact factor. By ‘surfacing’ their work in OERs they gain the following potential benefits:

- On the open web and therefore more accessible that in an academic repository

- Tracking and analytical data can be obtained

- Select target audiences

- Possibility of engaging with users via Web 2.0 feedback mechanisms

- Can use SEO techniques to drive up hits and online interest, the guides to SEO produced by Viv Rolfe at De Montfort are very informative and useful in this regard

- Can be a useful tool in building and maintaining individual, departmental and institutional scholarly profiles as well as a powerful method of community engagement

Interim feedback from Peter Robinson of Oxford in our online evaluation group meetings indicates that their OERs that contain research are indeed generating traffic and data that will count towards the next research assessment exercise. Another way of improving impact is to incorporate research outputs into Open Textbooks and assign ISBN numbers to such publications. This has the rather exciting potential to break down the barriers between the management and curation of research and learning resources both in the digital realm and in the academy – something that was the subject of discussion at the 2012 OER/OCWC conference in Cambridge.

### Research activities

Our focus groups and workshops provided our main ways of researching attitudes to OER/P and interest amongst students and staff as well as the level of digital skills and institutional infrastructure and support that was available.

### User testing

The main of user testing has been with our workshop participants in the development of the Open CourseBook format. Once the HTML5 authoring tool for the Open CourseBook is ready we shall carry out user testing with staff and students at the UAL and elsewhere. This differs fundamentally from existing content creation tools like Xerte or GloMaker in the following ways:

- Written entirely in HTML5 (both Xerte and Glomaker operate using Adobe Flash/Flex/Air engines to create content – Xerte has been retrofitted with a html5 player)

- Outputs HTML5 (including a zipped self contained website for offline use)

- Outputs ePub

- Responsive design will play on a wide variety of devices

- Breaks with the learning object philosophy and adopts a ‘publishing’ metaphor

## Immediate Impact

### What kind of difference has the project made to our partner institutions?

UAL:

- IPR policy review underway to accommodate OER/P engagement – interim report sates that there should be a ‘presumption of openness in academic activities’

- Senior management have requested a policy statement to be drawn up to encourage OER/P engagement by staff and students

- Senior management are actively exploring joining the OCWC

- Internal course handbooks are being redesigned into one consistent and simple format based on the ALTO UK Open CourseBook format

- CLTAD (Centre for Learning and Teaching in Art and Design) the project host organisation at the UAL has developed a postgraduate study option in  ‘Open Educational Practice’ for the UAL Continuing and Professional Development Framework and PG Cert. in HE Teaching – available to UAL staff and ADM teaching staff in the UK

- CLTAD management have realised that OER/P engagement is a powerful educational development tool as it promotes deep reflection and are incorporating it into their strategic planning priorities

- The UAL is switching to a new VLE (based on Moodle) and it is being proposed, as a result of ALTO UK project, that the default ‘share’ option will be open. This means that the contents of all the courses will be open to all the staff and students – this is a large step for a highly collegiate institution like the UAL.

- As a part of the new UAL Moodle development it is proposed to encourage teachers to use the UAL learning resource repository (Filestore) to store their course content in and reserve the use of the course space in Moodle for student activities and teaching activities, this is quite a radical step

- The new VLE and the e-Portfolio system are being integrated with the UAL learning resources repository system. This will provide the ability for teachers and students to select relevant resources and release them to the world under a Creative Commons licence from within the VLE and e-Portfolio systems – thus lowering the threshold to OER/P engagement. This is as a result of the ALTO UK project being involved in the system design discussion at an early stage. It was also supported by the work of a JISC OERRI project ‘Portfolio Commons’ that developed the use of the SWORD protocol to implement this.

Kirklees College

- The Applied Arts Dept. are using the approaches we used in our workshops and the Open CourseBook experience to redesign their ceramics courses for revalidation and they are exploring more flexible form of delivery

- Are intending to produce and use more online video and use what they have produced in the project with their own students. First year students are now routinely videoing demonstrations by their tutors and technicians and their work in the studio

- Taking a more organised approach to learning resource management – using file naming conventions and organising folders

- Now aware of the Creative Commons licence system and using it

Heriot Watt University, School of Textiles and Design

- Staff are using the approaches we used in our workshops and the Open CourseBook experience to redesign courses to cope with the effect of redundancies – by enabling more effective and consistent representation and sharing of courses and learning resources. Instructional videos and other materials created in the project are going to be used with students during this academic year as a way of maintaining quality and extending study opportunities outside the workshop see this link for an example.

- Flexible delivery options and course redesign using the lesson learnt during this project are being actively explored to cope with a rapidly changing market for these subjects.

Brighton

- Staff at the HEA ADM subject centre (now closed) at Brighton had the opportunity to carry out OER/P awareness-raising and focus group work in their own institution, using the techniques developed in their involvement in the two previous OER programmes.

- As part of their involvement in the ALTO UK project the ADM centre organised a national UK Art OER conference ‘Drawing on All Resources’ (please see the outputs section above), which was a great success and demonstrated a need for shared UK HE Arts online platform. This has put OER/P firmly on the agenda at Brighton where discussions are underway to incorporate a commitment to OER/P engagement into institutional policy.

- Brighton University has agreed to continue supporting the online ADM community magazine activities of the old ADM centre and we are in discussion with them about how this might be incorporated into a national shared online service for the UK ADM sector, as envisaged in the original ALTO UK project proposal.

Publishers

- Both publishers were surprised at the size of the FE market for ADM subjects and in the past had been focussing more on HE, as it was more ‘visible’ to them. Both are interesting in using future involvement both as a marketing tool and as a way of gaining market intelligence.

Bright Lemon

- Prior to this project Bright Lemon were unaware of the OER movement and during this project they have gained a greater insight and are now examining this area as a potential future market.

### How has the wider community benefitted from our project?

- Our Open CourseBook format would seem to provide a relatively easy to use and sustainable path for busy academics to create OERs as it uses a structured template to present existing content and benefits from the user-friendly metaphor of a book. For endangered ‘making’ subjects such as ceramics and textiles this looks like a promising means to be able to play a part in the ‘capture’ of the expertise to teach these subjects, in order to preserve them for the future.

- Converting courses in some ADM subjects into OERs, especially in the ‘making’ disciplines (such as ceramics and textiles) and fine art presents some challenges due to a shortage of traditional didactic content compared to STEM subjects. However, we have found that the use of rich media, particularly video, is good for capturing the teaching of technical processes. In addition we have found that using student work and testimonies (on video and in print) can help to capture and illustrate the hidden and invisible elements of teaching and learning on these courses in a useful and meaningful way

- Working with the publishers has been very interesting and useful and, in common with the other OER phase 3 projects that have a publisher connection, we think this could help develop a ‘mixed economy’ for supporting sustainable OER/P activities in the future. The OER Phase 3 ‘publisher group’ are intending to keep in contact about this and present at the OER13 conference

### What evidence do we have for this?

- Interviews

- Focus groups

- Workshops

- Observations

- Discussions with senior management

- Outputs and Outcomes

- Reports in the Appendix

### How has the project changed the attitudes of our stakeholders?

- Senior management at the UAL and Brighton are now much more engaged with the OER agenda and are putting it into their strategic planning activities

- Senior Management at Kirklees College Heriot Watt University, School of Textiles and Design are now aware of the OER agenda and community together with the potential benefits

- Students, at all the academic partners have been involved in courseware creation and consulted through focus groups. There is now a wider awareness amongst students about OERs and the benefits to be derived from them, although there is much more to be done in this area

- Academic Teachers at the academic partners have been involved in the project and in creating OERs and discussing them through focus groups. At two of the academic partners no one had heard of Jorum, OERs, or Creative Commons licences so awareness has been greatly increased, although there is much more to do

- Information Professionals (this applies mainly to the UAL as the project was using UAL’s infrastructure) have been involved in consultations with the project manager. There is recognition that the support for hosting and managing institutional learning resources is a new departure for the IT unit and that it needs to be factored into strategic planning. The cloud feasibility study carried out by the project is being discussed to compare internal and external hosting and support options and costs.

- OER Creators/Owners/Publishers. Students and staff involved in this project are now much more aware of the IPR, Copyright and Privacy issues involved and how they need to be attended to early on in the process. The publisher partners are more amenable to releasing some of their content under Creative Commons licences and like the idea of a project like this being a ‘sandpit’ to explore options and new market possibilities – we are exploring continuing the relationship to facilitate this for mutual benefit.

## Future Impact

### Who/What will be impacted?

- Future students at the UAL should benefit from:

  - Access to a growing number of Open CourseBooks that help them to make more informed course application choices and result in fewer students dropping out of course and greater student satisfaction ratings

  - Redesigned course handbooks that are simple and more consistent

- Endangered subjects will benefit from a simple and scalable means of capturing and preserving knowledge by using the Open CourseBook template

- A UAL IPR policy that will be clearer, less ambiguous, that specifically recognise OER/P as a scholarly activity and makes provision for it

- Researchers and institutions using OER/P engagement as a way of publicising research activities and outputs to support the impact factor in the REF,

- Marketing: OER/P can be an effective marketing tool for international and UK students and help students make more informed course decisions by seeing what actually happens in the courses they are considering applying to

- Teachers will have a simple means of creating OERs by using the Open CourseBook template that will also double up as a course redesign tool

- Publishers will be able to benefit from exposure to new markets (particularly FE and community education) and experiment with different models for OER engagement.

### Tracking this impact?

- Number of OERs published

- Google Analytics

- Repository analytics

- Continuing focus group work and consultations at the UAL and elsewhere

- Publicity, including Web2.0 feedback

# Conclusions

## General conclusions

### OER/P as a Driver for Change

The project was ambitious given the range and scale of the different activities in the short timescale as well as the differences in teaching that exist in the practice based disciplines of art and design in contrast to more ‘academic’ content-centric subjects. One of the project participants describes this difference as follows:

“Again, for those new to art and design subjects, it should be borne in mind that each student is endeavouring to find their own 'voice', so much teaching is on a one-to-one basis rather than through mass-delivery to a class whose members are expected to hold a common, single view. For example, a course teaching people to become opticians would want every student to have the same understanding of their subject - there is no room for an individual 'take' on how the laws of optics work. The reverse is of course true for arts subjects - society requires that practitioners create an individual view of things, and it is this uniqueness that is valued.”

Mark Clough, Kirklees College

The project has made a powerful step forwards for OER/P engagement in the UAL and amongst the partners and the ADM community in general. It has also explored some innovative solutions to sustainability in this sector. The idea of a creating a shared service to provide an online space for Art Colleges to work and benefit from the OER/P ‘economy’ is a viable one (from feedback received) and needs to be explored further.

The underlying educational philosophy governs how technology may be used in the educational process. Peter Dicken (2010) provides a useful insight into how our different conceptions of knowledge affect how it can be shared; he splits knowledge into 2 types:

1) Codified (or explicit): the kind that can be expressed formally in documents, plans, drawings, software and hardware etc.

2) Tacit: deeply personalized knowledge possessed by individuals is virtually impossible to make explicit and communicate to others

As Dickens observes, this distinction is fundamental to understanding the role of space and place in the technological diffusion of knowledge, with tacit knowledge having a very steep ‘distance-decay’ curve, while codified knowledge can be projected relatively easily across time and space. But, Dickens also cautions, this distinction can change in a number of ways that can make tacit knowledge more easily exchanged at a distance. One way that springs to mind that may be used to communicate tacit knowledge is the use of rich media, such as video or animations, that convey a sense of ‘being there’ and can have a persuasive rhetorical power to convey not just ideas and concepts but also affective and cultural factors (Laurillard, 2002).

Another, more radical, observation is that in higher education in Art and Design much tacit knowledge perhaps isn’t really tacit at all. Rather, the assertion that the knowledge involved is tacit may be a strategy to preserve the mystery and exclusiveness of the ‘secret garden’ of formal higher education. Rowles (2010), in a recent influential study, discusses this tendency to mystification when examining the current state of art education in a series of interviews with course leaders from leading London Art Colleges and discusses the tensions between the explicit and implicit in educational practice in the sector as well as the connections to the underlying cultures and values of those involved. As Dicken implies, the future of OER/P in the Art and Design sector will be to be determined by the underlying educational and cultural values of those involved. Into this situation the open education agenda can be a form of creative positive disruption that helps us to rethink aspects of our activity that are long overdue for revaluation.

OER/P engagement provides a source of ‘systemic disruption’ in our institutions which has powerful effects in a number of related dimensions:

- Teaching, disciplinary and institutional cultures - in relation to transparency and accountability

- IPR awareness and policy

- Technical Infrastructure

- Management structures

- Pedagogy

- Marketing

- Institutional Strategy

- Digital Literacy

This disruptive effect is potentially very useful to those involved in instigating and managing change in educational institutions. Linking OER/P engagement to change management is a useful strategy to employ and some studies and toolkits to support this would be useful (linked to previous work). There is evidence emerging from the JISC Curriculum Design programme to support this view; the Ulster ‘Viewpoints’ project and Greenwich ‘Supporting Responsive Curricula’ project for instance.

## Conclusions relevant to the wider ADM community

OER/P engagement is a powerful driver for positive change in HE/FE and encourages greater accountability and transparency – important factors in the current economic and political climate and can help in public relations. For the ADM subject community this can provide a valuable marketing and collaborative opportunity in the UK and internationally that could also bring the following benefits:

- OER/P related activities should continue to be supported, as it provides a powerful way of driving the reform and opening up of higher and further education and the cultural change needed to support this.

- The growing amount of openly licensed content helps provide an efficiency and value for money argument, which is important in the current economic climate.

- Use OERs to help students make more informed choices. There seems to be emerging evidence (from colleagues at Oxford, Falmouth, Open University) that students are using OERs to assess their choice of HE applications, making a successful choice and transition into higher education more likely

- Involvement with OER/P can provide a good basis for the development of flexible and distance learning capacity in the HE/FE sector as it involves developing many of the essential skills and capacity required (i.e. pedagogic design, shareable representation of the curriculum and effective digital resource management)

- In future work related to OER creation in the arts it would be good to extend the use of student work and testimonies to include input from teachers about their teaching intentions as well as more of a dialogue with students to capture the dialectical and iterative process of teaching and learning in these subjects – especially the development of an individual aesthetic by the students. The sketchbook videos produced by Kirklees College (link) provide a nice example of this.

## Conclusions relevant to JISC / HEA

Arguably, the successive OER programmes have had a greater visible effect on the sector than any previous initiative. Continued support for work in this area would make great sense in acting as a powerful driver for the cultural change that is needed to make effective use of technology in teaching. OER activity also provides very visible ‘evidence’ of JISC’s investment and activities to its stakeholders and the general public.

# Recommendations

## General recommendations Arising from the Project - UAL

- Create a UAL ‘how to’ handbook for OERs in the arts

- Create exemplars that demonstrate how OERs (including Open TextBooks) can be used to increase impact ratings for research

- Take an endangered subject and create a series of OERs to support the development of flexible delivery in that subject and create a case study

- Continue the development of the HTML5 authoring tools for the Open CoursBook format and seek to collaborate on this with others who have expressed an interest in using the tool. Investigate integrating the XCRI standard into the authoring tool and examine the work of the JISC Curriculum Design programme for tools and methods to incorporate into the development process

- Seek funding and collaboration opportunities to develop the ONCE architecture and development road map as set as out in the conference paper published by Firenze University (http://alto.arts.ac.uk/943/)

- Identify UAL archives to be digitised, using Creative Commons licences, to support new digital research opportunities and incorporate the archive contents into OERs

- Use SEO optimisation techniques to drive traffic to our OER sites and collaborate

## Recommendations for working with the wider ADM community

- The ‘Drawing on All Resources’ conference indicated that there was a need for a shared UK online service to support OER/P engagement in the arts. We should explore with Brighton how we might do that and seek funding to do so.

- Collaborate with the Humbox community to learn from their experience in building an online OER community

- Collaborate with Coventry University School of Art and Design OER initiatives as they are doing work with MOOCs that makes use of the existing Web 2.0 infrastructure that would be very useful to the sector in the future.

## Recommendations for JISC

Following on from discussions at the annual OCWC/OER conference in Cambridge in 2012 and discussions in the OER 3 programme evaluation meetings, we feel it is time to propose that the management and curation of research outputs and data and learning resources should not be separated in our institutions and that both come under the open access agenda umbrella. In this regard, it is important to understand that the creation, management and sharing of learning resources in our institutions has by ‘custom and tradition’ been left to individual teachers. Outside of specialist distance-learning units there is no institutional tradition of managing learning resources in-house. Tech-centric and information management inspired initiatives have not succeeded as the experience of attempts to introduce learning objects and top-down technical standards have shown.

What would be useful is to explore is how research and learning resources can be managed together and to challenge the dominant, and rather narrow, information management/curation paradigm that has dominated discussions in this area to date. A useful avenue to explore, in general, and to provoke creative dialogue and progress in this area is to emphasise:

- Open access facilitation – probably the most powerful driver we have

- Knowledge management – as opposed to information management

- Use of information retrieval techniques

- Use of product design techniques – to design more effective systems and bring in different communities of designers and developers to provide fresh perspectives

- Support and promote the development of simple embedding mechanisms (like those used by YouTube, Flickr, and WordPress) in existing academic repository systems. A very basic web page that illustrates this in action can be found at http://www.digitalinsite.co.uk/jorum/ where example of resources from the Jorum and EdShare (UAL) repositories have been directly embedded into a web page – something that is not currently easy to do.

- Publicise the benefits of OER/P in relation to supporting the impact factor ratings in the REF

# Implications for the future

What are the implications of our work for other professionals in the field, for users, and for the community?

- Access to more OERs in Art and Design

- The use of student work and testimonies to illustrate learning processes in Art and Design

- Better authoring tools

- Improved course information

- More informed student course selection leading to better satisfaction and retention rating for institutions

- Investigation of better storage and management options for learning resources

- A viable method for knowledge preservation in endangered subjects

- Cooperation with commercial publishers to create a hybrid OER economy that is mutually beneficial

New development work could be undertaken to build on our work or carry it further?

- Further development of the HTML5 authoring tool and the rest of the ONCE architecture

- Development of a shared UK OER publishing and collaboration platform

- Investigation of international collaboration possibilities (please see the Appendix)

- Create exemplars of OERs that improve research impact, with case studies

What is the sustainability of our project outputs? How are things going to work now the funding is over?

- The outputs are all openly licensed and placed in our 2 institutional OER services (Filestore and Process.Arts), which have been adopted as permanent core university services.

- The university (UAL) is developing a commitment to OER engagement in its policy and is going to join the OCWC

- A strategy is being developed to develop long-term core funding for OER/P activities at the UAL

Long Term Management

- Long term contact is Nancy Turner, Associate Dean: Learning and Teaching Development, CLTAD, nancy.turner@arts.ac.uk

- Outputs are openly licensed and stored in the open learning resources repository (Filestore) or social media platform (Process.Arts)

- Software will be licensed under an open source licence and placed in a code repository (GitHub)

References

Dicken, P. (2010) Global Shift: Mapping the Changing Contours of the World Economy, Sage Publications

Lambe, P. (2007) Organising Knowledge: Taxonomies, Knowledge and Organisational Effectiveness. Oxford: Chandos.

Laurillard, D. (2002). Rethinking University Teaching. Abingdon: Routledge and Falmer

Mayes, J.T, Dineen, F., Mckendree, J., & LEE, J. (2001) Learning from watching others learn. In C.Steeples & C.Jones (Eds) Networked Learning: Perspectives and Issues. Springer: London,

Moon J (2002) The Module and Programme Development Handbook: a practical guide to linking levels, outcomes and assessment, Abingdon: Routledge and Falmer

Mumford, E. (1995) Effective Systems Design and Requirements Analysis: The ETHICS Approach. Basingstoke: Macmillan.

Rowles, S. (2010) 11 Course Leaders 20 Questions: A Collection of Interviews with 11 London BA Fine Art Course Leaders, Q Arts London: London Student and Graduate Artist Forum http://www.q-artlondon.com/

Sharples, M., Jeffery, N., du Boulay, J.B.H., Teather, D., Teather, B., and du Boulay, G.H. (2002) Socio-cognitive engineering: a methodology for the design of human-centred technology. European Journal of Operational Research, 136, 2,

Wenger, E. (1998) Communities of Practice. Cambridge: Cambridge University Press.

Wenger, E., White, N., Smith J.D., (2009) Digital Habitats: stewarding technology for communities, Portland.

# Appendices

## Brighton OER Study

Please Consult the PDF document ‘ARTS-OER-Brighton-Final-Report.pdf’

## ALTO UK / DIAL Open Educational Practice Update

Please consult the Word document ‘DIAL update – Open education at UAL.docx’

## ALTO UK Evaluation Report

Please consult the Word document ALTO UK Evaluation Report.docx

## HEA International OER Collaboration Study

Please see the Word document UAL ‘HEA OER INT Final proposal-19-9-2012-1500.docx’

http://arts.brighton.ac.uk/projects/networks/issue-18-july-2012/drawing-on-all-resources-developing-open-educational-practice-in-art,-design-and-media

http://process.arts.ac.uk/

http://www.hefce.ac.uk/news/newsarchive/2012/name,69544,en.html

http://www.imsglobal.org/learningdesign/

See: http://www.jisc.ac.uk/curriculumdesign; Design Studio Wiki; Outputs: Final Synthesis Report

http://en.wikipedia.org/wiki/Low-residency_program,  http://www.vanadia.com/liveandlearn/links/, http://www.massart.edu/academic_programs/fine_arts_2d/low-residency_mfa_provincetown.html

http://catalog.uarts.edu/preview_entity.php?catoid=5&ent_oid=125&returnto=107

http://www.oca-uk.com

http://www.uhi.ac.uk/en/courses/hnc-equine-studies

http://www.sicklecellanaemia.org/teaching-resources/resources/scooter80/SCOOTER80a_SEO_Guidelines.pdf

http://www.jisc.ac.uk/fundingopportunities/funding_calls/2011/11/oerrapidinnovation.aspx

http://www.jisc.ac.uk/whatwedo/programmes/ukoer3/rapidinnovation/portfoliocommons.aspx and http://portfoliocommons.myblog.arts.ac.uk/

http://www.jisc.ac.uk/whatwedo/programmes/elearning/curriculumdesign/viewpoints.aspx

http://www.jisc.ac.uk/whatwedo/programmes/elearning/curriculumdesign/ugflex.aspx

http://www.xcri.co.uk/

Hoel, T. (2010) If we are concerned with what we standardise we should be able to describe it for people to understand, online at http://hoel.nu/wordpress/?p=426, also see The Future of Interoperability and Standards in Education: A white paper. By Li Yuan, Scott Wilson, Adam Cooper and Lorna M Campbell published by JISC CETIS, which provides a good reflective self analysis of shortcoming in theory and practice in this area.

P. Lambe, Organising Knowledge: Taxonomies, Knowledge and Organisational Effectiveness. Oxford: Chandos, 2007.

http://en.wikipedia.org/wiki/Information_retrieval