JISC WORK PACKAGE

Before completing this template please note:

- The Project Management Guidelines have detailed instructions for preparing project plans and work packages..

- Please expand tables as appropriate.

- Fill in the information in the document header – project name, document version, and date.

- Text in italics is explanatory and should be deleted in completed documents.

| ##### WORKPACKAGES | #### Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O |
| WP1: Set Up |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP2: Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP3: Team Formation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP4: Action plan target |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP5: Web platform |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP6: Evaluate impact |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP7: Resource dev |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP8: Group development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP9: Sustainability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestones |  |  |  | 1 |  | 2 | 3 |  | 456 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Project start date: Nov 2011

Project completion date: Nov 2013

Duration: <24> months

| ## YEAR 1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ##### WORKPACKAGE 1: Set Up Objective: |  |  |  |  |  |
| - Establish project implementation and governance structures | Nov 11 | Dec 11 |  |  |  |
| - DIAL Project Blog/Wiki and identity | Nov 11 | Dec 11 | Temporary/informal project blog prior to main blog webspace being developed |  | PM |
| - Identify groups for 3 month group pilot | Nov 11 | Jan 12 | Evaluate processes and baseline current practice, help to start/embed the project working with up to 5 self identify groups. | 1 | PM, project team (PT) |
| - Baselining and evaluation research | Nov 11 | Jan 12 | Research and feedback, explore synergies for ongoing baselining and evaluation |  |  |
| - JISC project Base lining | Nov 11 | Jan 12 | JISC baseline report (project baselining to continue) | 1 | PM |
| - Submit Project Plan | Nov 11 | Jan 12 | Project plan |  | PM |
| - Project plan on institution website | Jan 12 | Feb 12 | UAL project website | 1 | PM |
| ##### WORKPACKAGE 2: Project Management Activities Objective: |  |  |  |  |  |
| - Project Management Evaluation, Budgeting and Report Writing, Convening meetings arranging dissemination etc. | Nov 11 | June 12 | Reports, Board Minutes, Budgets, dissemination events and activities. Project activities completed on time and within budget |  | PM |
| - Meet with project partners | Nov 11 | Jan 12 | Meeting schedule, communication plan. Key staff on board, form DIAL operational team. Establish UAL Project contacts and base in each college. Undertake team building and technical development with the digital literacies support team members, based on experience and relevant research |  | PM |
| ##### WORKPACKAGE 3: Project Team and DIAL group Formation Objective: |  |  |  |  |  |
| - Orientation, DIAL operational team group development and access to information (JISC wiki and project blog) Visits, Discussions | Nov 11 | Mar 12 | Project staff briefed, DIAL operations group active engagement through project Wiki and blog participation. |  | PM |
| - Core groups of self identified DIAL communities | Nov 11 | June 12 | Identify and establish contact with university communities to participate (Yr1) 16 DIAL ‘resident’ groups. Establish mini projects, resource construction and collaborative training and mentoring in all participating communities. Developmental resources | 4 | PM, PT |
| - Engage with industry/sector partner, form group | Mar 12 | June 12 | Visit sector bodies and employers, form industry/sector partner group | 4 | PM, PT |
| - Initial planning for integration of Institutional, Industry/sector and Alumni groups. | Mar 12 | June 12 | Three way formation of a Institutional, Industry/sector partner and Alumni graduate DIAL operational group |  | PM |
| ##### WORKPACKAGE 4: Negotiate action plan targets with DIAL groups Objective: |  |  |  |  |  |
| - Hold Focus Group meetings in all institutions with all groups collect information | Dec 11 | Mar 12 | Collaboration with UK OER 3 ALTO UK project, support JISC and ongoing baselining, Conduct group and individual interviews with all Yr1 stakeholders to establish current skills levels, anxieties and aspirations. Recordings and transcriptions |  | PM, Duna Sabri (DS), PT |
| - Develop group action plans | Mar 12 | Apr 12 | Produce Focus Group reports | 3 | PM, DS |
| ##### WORKPACKAGE 5: Establish DIAL Web spaces, community group media & communication online platform Objective: |  |  |  |  |  |
| - DIAL community website - adapt code from existing drupal software (process.arts) redevelop and test with users / Commission Web server and install software | Dec 11 | Mar 12 | Install an Initial prototype, followed by ongoing agile development with users. | 2 |  |
| - DIAL website long term integration with UAL future web and institutional VLE and web space new infrastructure plans | Mar 12 | July 13 | Strong communication and integration plan with the UAL web environment team and new VLE and institutional website. | 5 |  |
| ##### WORKPACKAGE 6: Evaluate Impact, from a range of perspectives (against project aims and objectives, institutional and course level impact, cultural change and sustainability for the future) Objective: |  |  |  |  |  |
| - Agree structure of evaluation with DS | Nov 12 | Dec 12 | Research plan |  | SRO, DS |
| - Commence evaluation research | Dec 12 | Jan 12 | Research |  | DS |
| - Submission of Year 1 Evaluation Report | June 12 | June 12 | Report | 6 | DS, PM |
| - Revision of project methodology and processes, based on interim evaluation |  | June 12 | Revised Project Method |  | PM |
| ## YEAR 2 |  |  |  |  |  |
| WORKPACKAGE 7: Resource development Objective: |  |  |  |  |  |
| - DIAL resources |  |  |  |  |  |
| - OER |  |  |  |  |  |
| - Resource reuse |  |  |  |  |  |
| #### WORKPACKAGE 8: DIAL group and Communication development Objective: |  |  |  |  |  |
| - Communication development |  |  |  |  |  |
| - Connectivity inter college communication |  |  |  |  |  |
| - Infrastructure |  |  |  |  |  |
| - Culture change |  |  |  |  |  |
| #### WORKPACKAGE 9: Sustainability Objective: |  |  |  |  |  |
| - UAL DL policies and practices integration |  |  |  |  |  |
| - UAL Web environment integration |  |  |  |  |  |
| #### WORKPACKAGE 10: Objective: |  |  |  |  |  |

Members of Project Team:

| Name | Role |
| --- | --- |
| Shân Wareing | Director |
| Chris Follows | Project Manager |
| Lindsay Jordan | Operational Team & Evaluator (Educational Developer) |
| Duna Sabri | Evaluator (Senior Research Officer) |
| John Jackson | Operational Team (Educational Developer) |
| Philip Ratcliff |  |
| John Casey | Operational Team (OER and ALTO) |
| Jessica Crilly | Operational Team )Development & Learning , HR, D&L) |
| David Bracegirdle | Operational Team (Information services and Library) |
| Stephen Beddoe | Operational Team (Student Enterprise & Employability Service) |
| Ben Westhead | Operational Team (Students Union) |