: Final Project Proposal: Action Plan & Timetable

To be completed by the Student

| Name: | Adrienne Santos |
| --- | --- |

| Project Title: | Excavate to discover |
| --- | --- |

| PART 2/3 Week | Week commencing: | Action Plan |
| --- | --- | --- |
| 1 | 31.01.11 | Initial research - Begin to look for contextual material available. WCA Library, UAL online library catalogue, SOAS online library catalogue, - Discuss ideas with tutor. Take in suggestions, ask for starting points of research, guidance in time management. Valuable hindsight of experience. Thursday 10th February: FPP final deadline. 2 copies handed to area leader |
| 2 | 07.02.11 | Research - Begin reading contextual material. - Refer to bibliography: Kerlogue, F.; Rawson, P. Organize trip to Pitt Rivers Museum, Oxford |
| 3 | 14.02.11 Assessment Week | Research - Read contextual material. - Go to SOAS Library. Extensive collection of books on art in the Philippines and Southeast Asia. - Go to Philippine Embassy. Small library that could be useful. Find out about any Filipino artists coming to / residing in England. - Go to Pitt Rivers Museum, Oxford. Photograph and draw artefacts. Collect both visual and contextual inspiration. Thursday 17th February: Part 2 Assessment. With Annie. Establish personal stance in work. What questions will I ask? What do I want to explore? Why am I doing this, why am I here? |
| 4 | 21.02.11 | In studio - Exploration on subject matter through drawing. Inspired by material read and seen so far. - Drawing from drawings. Beginning of realization from 2D to 3D. - Create maquettes if appropriate - Catch ideas on paper by having sketchbook nearby all the time!! Out of studio - Continue reading research - Maintain reflective disposition throughout project. Look through photos taken from each day. Write in reflective journal. |
| 5 6 7 | 28.02.11 07.03.11 14.03.11 | (Move on to this only if ready to start making final piece. If not, repeat last week’s agenda only for week 5.) In studio - Monday and Tuesday: make for firing - Tuesday night: bisque firing - Wednesday: research if necessary / make for next week’s firing - Thursday/Friday: make for next week’s firing, glaze bisque work - Thursday/Friday night: stoneware firing Out of studio - Maintain reflective disposition throughout project. Look through photos taken from each day. Write in reflective journal. - In case of uninspiration: go find it. |
| 8 | 21-27.03.11 | Wrap everything up! Write self-assessment form. Prepare work for crit. |